## Summary
Spain 2027 plan summary
Today
Deadlines: open items by workstream
Workstream | Open | Overdue | Due in 14 days | Done
Programs
Immigration
Tax
Income
Trip
Outreach
Kindergarten
Spanish
Move
Housing
Work
Dog
Total
Monthly actions: open items by month
Month | Open | Done
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
2027-04-01
2027-05-01
2027-06-01
2027-07-01
2027-08-01
2027-09-01
2027-10-01
Formulas:
Overdue = COUNTIFS(Deadlines!$B2:B34,[Workstream],Deadlines!$E2:E34,"<>Done",Deadlines!$C2:C34,"<"&TODAY())
Due in 14 days = COUNTIFS(Deadlines!$B2:B34,[Workstream],Deadlines!$E2:E34,"<>Done",Deadlines!$C2:C34,">="&TODAY(),Deadlines!$C2:C34,"<="&(TODAY()+14))

## Deadlines
Task | Workstream | Due | Days left | Status | Type | Confidence | Source, checked | Notes
ELISAVA Design for Responsible AI, 2026 intake application deadline (past) | Programs | 2026-09-08 |  | Done | EXTERNAL | confirmed | User, 2026-09-09
Client and contract inventory complete with end dates and monthly value | Income | 2026-09-30 |  | Not started | TARGET | assumed | This plan
October trip dates fixed and flights booked | Trip | 2026-09-30 |  | Not started | TARGET | assumed | This plan
Verify which Spanish consulate covers Colorado | Immigration | 2026-09-30 |  | Not started | TARGET | assumed | This plan
Income evidence window opens: every month from here to filing must show consistent deposits at or above threshold | Income | 2026-10-01 |  | Not started | RELATIVE | assumed | Chat 1: 3 to 6 months before filing
Outreach sent to Salesforce partners in Barcelona, meetings requested for trip | Outreach | 2026-10-15 |  | Not started | TARGET | assumed | This plan
New EU pet certificate forms take effect; any dog travel after this date uses the new forms | Move | 2026-10-01 |  | Info | EXTERNAL | confirmed | APHIS via search, 2026-09-09
EU Business School Barcelona open day, 16:00 to 18:00 | Programs | 2026-10-23 |  | Not started | EXTERNAL | confirmed | euruni.edu events page via search, 2026-09-09
Barcelona trip: neighborhood, schools, kindergartens, agencies, partner meetings | Trip | 2026-10-01 |  | Not started | TARGET | assumed | User, 2026-09-09 | Month only. dates TBD
Spanish milestone: Language Transfer complete, 1200 words, 20-minute tutor conversation | Spanish | 2026-10-31 |  | Not started | TARGET | confirmed | Spanish plan
All shortlisted programs contacted; 2027 intake status and deadline recorded | Programs | 2026-10-31 |  | Not started | TARGET | assumed | This plan
Tax advisor consult done; Beckham path decided (administrator route or standard autonomo) | Tax | 2026-11-15 |  | Not started | TARGET | assumed | This plan
If administrator route: LLC operating agreement amended | Tax | 2026-11-30 |  | Not started | TARGET | assumed | Chat 1
TBS Education Barcelona MSc application deadline for 2027 intake (2026 intake closed 2025-12-12) | Programs | 2026-12-01 |  | Not started | EXTERNAL | assumed | Search snippet, 2026-09-09 | Month only. assumed
Contracts signed covering at least Jan to Dec 2027 at or above threshold | Income | 2026-12-15 |  | Not started | TARGET | assumed | This plan
Health insurance policy selected | Immigration | 2026-12-31 |  | Not started | TARGET | assumed | This plan
FBI background check ordered | Immigration | 2026-12-31 |  | Not started | TARGET | assumed | Chat 2
Spanish milestone: 2500 words, can handle landlord or bank call | Spanish | 2027-01-31 |  | Not started | TARGET | confirmed | Spanish plan
Apostille chain started for all documents | Immigration | 2027-01-31 |  | Not started | TARGET | assumed | Chat 1
Catalonia school preinscripcio 2027-28 for I3 to I5; 2026-27 window was March 4 to 18. Late filing loses priority points | Kindergarten | 2027-03-01 |  | Not started | EXTERNAL | assumed | preinscripcio.gencat.cat via search, 2026-09-09 | Month only. early, assumed
Sworn translations ordered | Immigration | 2027-03-15 |  | Not started | TARGET | assumed | Chat 1
Visa packet complete | Immigration | 2027-03-31 |  | Not started | TARGET | assumed | Chat 1
DNV filed (consular EX-01) or in-country plan locked | Immigration | 2027-04-15 |  | Not started | TARGET | assumed | Chat 1
Spanish milestone: B1, unstructured conversation without English | Spanish | 2027-04-30 |  | Not started | TARGET | confirmed | Spanish plan
BTS Master in Digital Transformation and AI Leadership deadline for September 2027 intake | Programs | 2027-06-01 |  | Not started | EXTERNAL | assumed | Aggregator, 2026-09-09 | Month only. assumed
Arrival in Barcelona | Move | 2027-05-01 |  | Not started | TARGET | assumed | User | Month only. date TBD
Dog EU health certificate issued | Move |  |  | Not started | RELATIVE | confirmed | Chat 2 | Arrival minus 10 days
Empadronamiento registered | Move |  |  | Not started | RELATIVE | assumed | Chat 3 | Arrival plus 30 days
If in-country EX-11 route: must file within 90 days of visa-free entry | Immigration |  |  | Not started | RELATIVE | confirmed | Chat 1 | Arrival plus 90 days
Modelo 149 (Beckham) filed, only if eligible | Tax |  |  | Not started | RELATIVE | confirmed | Chat 1 | SS registration plus 6 months
ELISAVA 2027 intake application deadline | Programs | 2027-09-08 |  | Not started | EXTERNAL | assumed, same as 2026 | User, 2026-09-09
Program start | Programs | 2027-09-01 |  | Not started | EXTERNAL | not verified |  | Month only. or 2027-10
DNV renewal; income re-proven over prior 3 to 6 months | Immigration |  |  | Not started | RELATIVE | confirmed | Chat 1 | Filing plus 1 year (consular) or 3 years (in-country)
Formulas:
Days left = IF(OR([Due]="",[Status]="Done"),"",[Due]-TODAY())

## Monthly actions
Month | Workstream | Action | Due | Status | Notes
2026-09-01 | Income | Inventory every current client: contract end date, monthly value, entity type, country. | 2026-09-30 | Not started
2026-09-01 | Income | Gap analysis Oct 2026 to Dec 2027 against 5,400 to 5,900 USD per month. | 2026-09-30 | Not started
2026-09-01 | Income | Route all client deposits to one business account; invoice monthly. | 2026-10-01 | Not started
2026-09-01 | Programs | Record ELISAVA's answer: 2027 intake not confirmed (received 2026-09-09). |  | Not started
2026-09-01 | Programs | Email the seven new schools (BTS, TBS, EAE Barcelona, ESIC, IED, La Salle MSc, Comillas) for: 2027 intake deadline, syllabus with coding content, language, schedule, degree type, tuition. | 2026-09-30 | Not started
2026-09-01 | Programs | Verify each answer against the hard rules and move the program to shortlisted or eliminated. |  | Not started
2026-09-01 | Trip | Fix dates and book flights. | 2026-09-30 | Not started
2026-09-01 | Trip | Book accommodation in a candidate neighborhood. | 2026-09-30 | Not started
2026-09-01 | Trip | Request admissions meetings. | 2026-09-30 | Not started
2026-09-01 | Immigration | Verify which consulate covers Colorado. | 2026-09-30 | Not started
2026-09-01 | Immigration | Book NIE appointment; prepare EX-15, passport copy, fee 790-012. |  | Not started
2026-09-01 | Immigration | Check all three passports valid to at least May 2028. |  | Not started
2026-09-01 | Immigration | Pull LLC documents: articles, operating agreement, 3 to 6 months statements, contracts, invoices. |  | Not started
2026-09-01 | Immigration | Request health insurance quotes (full coverage, no copays, no waiting period). |  | Not started
2026-09-01 | Tax | Book the Spanish cross-border tax advisor consult (Beckham for LLC owner). |  | Not started
2026-09-01 | Spanish | Daily template. Start tutoring by week 3 of the plan if not started. |  | Not started
2026-09-01 | Dog | Vet: confirm microchip and rabies vaccine current. |  | Not started
2026-10-01 | Income | Evidence window opens 10-01: every month from now must show deposits at or above threshold. |  | Not started
2026-10-01 | Income | Pipeline list of retainer prospects. | 2026-10-15 | Not started
2026-10-01 | Income | Send retainer or extension proposals. | 2026-10-31 | Not started
2026-10-01 | Income | Ask the bank how to get stamped statements. | 2026-10-31 | Not started
2026-10-01 | Income | Log October deposits in the evidence log. |  | Not started
2026-10-01 | Outreach | Send Salesforce partner outreach. | 2026-10-15 | Not started
2026-10-01 | Outreach | Hold partner meetings during the trip. Log outcomes. |  | Not started
2026-10-01 | Kindergarten | Record the daughter's birth date and 2027 school year. | 2026-09-30 | Not started
2026-10-01 | Kindergarten | Ask the Consorci d'Educacio whether the March 2027 preinscripcio can be filed from abroad. | 2026-10-31 | Not started
2026-10-01 | Trip | EU Business School open day October 23, 16:00 to 18:00, if dates align. |  | Not started
2026-10-01 | Trip | Kindergarten and school visits requested. | 2026-10-05 | Not started
2026-10-01 | Trip | Agency and lawyer meetings requested. | 2026-10-05 | Not started
2026-10-01 | Trip | Itinerary and question lists. Trip minus 7 days. |  | Not started
2026-10-01 | Trip | Trip: neighborhood decision, university visits, kindergarten visits, agency meetings, partner meetings. |  | Not started
2026-10-01 | Trip | After the trip: write up decisions in plan/trip/october-2026-barcelona.md and update profile.md. |  | Not started
2026-10-01 | Programs | All shortlisted programs contacted; 2027 intake status and deadlines recorded. | 2026-10-31 | Not started
2026-10-01 | Programs | Start shared application assets: CV, diploma and transcript scans, passport scan. |  | Not started
2026-10-01 | Spanish | Milestone 10-31: Language Transfer done, 1200 words, 20-minute tutor conversation. |  | Not started
2026-11-01 | Income | Follow up on every open proposal. Log November deposits. |  | Not started
2026-11-01 | Tax | Tax advisor consult done; Beckham path decided. | 2026-11-15 | Not started
2026-11-01 | Tax | If administrator route: amend LLC operating agreement. | 2026-11-30 | Not started
2026-11-01 | Programs | Draft one motivation letter per program in plan/documents/. |  | Not started
2026-11-01 | Programs | Submit any application whose deadline falls before January. |  | Not started
2026-11-01 | Programs | Request recommendation letters where required. |  | Not started
2026-11-01 | Immigration | Identify self-employment proof documents (Schedule C and SE, or IRS transcript). Request IRS transcript. |  | Not started
2026-11-01 | Immigration | Choose immigration lawyer or agency from trip meetings. Get flat fee in writing. |  | Not started
2026-11-01 | Spanish | Phase 2: three tutor sessions per week, weekly monologue recording, Peninsular news audio. |  | Not started
2026-12-01 | Income | Contracts signed covering Jan to Dec 2027 at or above threshold. | 2026-12-15 | Not started
2026-12-01 | Income | Log December deposits. |  | Not started
2026-12-01 | Immigration | Health insurance policy selected. | 2026-12-31 | Not started
2026-12-01 | Immigration | Order FBI background check. | 2026-12-31 | Not started
2026-12-01 | Immigration | Order certified copies: marriage certificate, daughter's birth certificate. |  | Not started
2026-12-01 | Programs | Submit applications with December or January deadlines. |  | Not started
2027-01-01 | Immigration | Start apostille chain: notarize diploma and transcript, send to Colorado Secretary of State; apostille FBI check, self-employment proof, marriage and birth certificates. | 2027-01-31 | Not started
2027-01-01 | Programs | Interviews. Track decisions. |  | Not started
2027-01-01 | Income | Log January deposits. Confirm every 2027 contract is invoicing. |  | Not started
2027-01-01 | Spanish | Milestone 01-31: 2500 words, landlord or bank call. |  | Not started
2027-02-01 | Programs | Collect decisions, compare offers, accept and pay deposit where decided. |  | Not started
2027-02-01 | Immigration | Track apostille returns. Chase anything outstanding. |  | Not started
2027-02-01 | Income | Log February deposits. |  | Not started
2027-02-01 | Spanish | Phase 3: four tutor sessions per week, native media only, task-based rehearsal (apartment viewing, empadronamiento, NIE, pediatrician, school enrollment). |  | Not started
2027-03-01 | Kindergarten | Preinscripcio 2027-28 window (assumed early March) if filing from abroad is allowed. |  | Not started
2027-03-01 | Immigration | Sworn translations ordered from a MAEC-certified traductor jurado. | 2027-03-15 | Not started
2027-03-01 | Immigration | Visa packet complete. | 2027-03-31 | Not started
2027-03-01 | Immigration | Check certificate validity windows so nothing expires before filing. |  | Not started
2027-03-01 | Income | Log March deposits. Evidence window closes. Request stamped statements Oct 2026 to Mar 2027. |  | Not started
2027-03-01 | Housing | Book 1 to 3 month temporary furnished rental for arrival. |  | Not started
2027-04-01 | Immigration | File DNV (consular EX-01) or lock the in-country EX-11 plan. | 2027-04-15 | Not started
2027-04-01 | Immigration | Do not commit the move date until approval or a credible processing estimate. |  | Not started
2027-04-01 | Move | Household shipping quotes. Decide sell, store, or ship. |  | Not started
2027-04-01 | Move | Give notice on Denver housing per lease terms. |  | Not started
2027-04-01 | Spanish | Milestone 04-30: B1. Catalan passive exposure 15 minutes per day. |  | Not started
2027-04-01 | Dog | Book vet appointment for the EU health certificate at arrival minus 10 days. |  | Not started
2027-05-01 | Move | Dog EU health certificate within 10 days of travel. |  | Not started
2027-05-01 | Move | Arrive. Temporary rental. Empadronamiento within 30 days. |  | Not started
2027-05-01 | Move | If in-country route: file EX-11 within 90 days of entry. |  | Not started
2027-05-01 | Move | Start Catalan through the Consorci per a la Normalitzacio Linguistica. |  | Not started
2027-05-01 | Move | Two tutor sessions per week for the first month. |  | Not started
2027-05-01 | Kindergarten | Out-of-period placement request for the daughter. |  | Not started
2027-06-01 | Move | Police appointment: fingerprints, TIE. |  | Not started
2027-06-01 | Move | Bank account, Social Security registration, healthcare registration. |  | Not started
2027-06-01 | Move | Sign 12-month lease. |  | Not started
2027-06-01 | Tax | If eligible: Modelo 149 within 6 months of Social Security registration. Otherwise RETA registration. |  | Not started
2027-07-01 | Programs | Prepare ELISAVA 2027 application materials if the intake is confirmed. |  | Not started
2027-07-01 | Tax | Confirm Modelo 149 or RETA done. |  | Not started
2027-08-01 | Programs | Submit ELISAVA application ahead of the assumed 09-08 deadline. |  | Not started
2027-08-01 | Kindergarten | Confirm September placement. |  | Not started
2027-09-01 | Programs | ELISAVA deadline 09-08 (assumed). September-intake programs start. |  | Not started
2027-09-01 | Kindergarten | Daughter starts school. |  | Not started
2027-09-01 | Work | Shift work hours to local time. |  | Not started
2027-10-01 | Programs | October-cycle programs start. Confirm on-campus schedule. |  | Not started
2027-10-01 | Immigration | Note renewal date and the 3 to 6 month evidence window before it. |  | Not started

## Programs
Program | University | City | Status | Deadline | Missing items | Last checked
Master in Design for Responsible AI | ELISAVA (UVic-UCC) | Barcelona | Applying. Primary target. School not yet committed to running a Sept 2027 intake. | Not verified | Confirm 2027 intake runs; deadline; motivation letter; meeting in Oct 2026 | 2026-09-08
Master in AI for Business | EU Business School | Barcelona | Shortlisted, apply | Not verified | Deadline; syllabus re-check; meeting in Oct 2026 | 2026-09-08
Master in AI for Management | GBSB Global | Barcelona | Shortlisted with conflict, see program file | Not verified | Resolve credential conflict; verify analytics modules are no-code; meeting in Oct 2026 | 2026-09-08
Master in Public Policy, AI and Digital Transformation | IE University | Madrid | Shortlisted with conflict, see program file | Not verified | User decision: public policy was ruled out on 2026-08-07 | 2026-09-08
Expert Diploma in Responsible Management of AI | UPF-BSM | Barcelona | Meeting only, not a master | Not verified | Book meeting in Oct 2026 | 2026-09-08
Master in Digital Transformation and AI Leadership | Barcelona Technology School | Barcelona | New, to verify | Not published; about June 2027 assumed | Syllabus, degree type, schedule, deadline; meeting in Oct 2026 | 2026-09-09
MSc Digital Transformation and AI for Business | TBS Education | Barcelona | New, to verify | Not published; about Dec 2026 assumed from 2025-12-12 | Senior fit, schedule, internship, deadline; meeting in Oct 2026 | 2026-09-09
Master en IA Aplicada a Negocio | EAE Business School | Barcelona | New, coding and language unresolved | Not published | Syllabus, language, official status, deadline | 2026-09-09
Master en Inteligencia Artificial (MIA) | ESIC | Barcelona | New, coding unresolved | Not published | Syllabus, language, deadline | 2026-09-09
Master in Design for AI | IED Barcelona | Barcelona | New, to verify | Not published | Syllabus, coding, language, schedule, deadline; meeting in Oct 2026 | 2026-09-09
MSc AI for Business Management | La Salle (URL) | Barcelona | New, coding unresolved | Not published | Syllabus, coding, schedule, deadline | 2026-09-09
Master en Filosofia de la IA | Comillas | Madrid | New, Madrid only | Not published | Format, language, official status, deadline | 2026-09-09

## Income log
Threshold EUR per month (2026 basis, family of three) | 4275
Exchange buffer | 15%
Target USD per month
Source: chat 1, 2026-08-07. Threshold rises with the SMI each year; update B1 when the 2027 figure is published.
EUR to USD rate used for target | 1.144
Rate source: chat 1, 2026-08-07. Update to the current ECB rate.
Month | Gross deposits USD | EUR at month-end rate | Rate used | Above threshold | Non-Spain share | Notes
2026-10-01 | 6000 |  | 1.144 |  | 100% | Example values. Replace with real October deposits.
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
2027-04-01
2027-05-01
2027-06-01
2027-07-01
2027-08-01
2027-09-01
2027-10-01
2027-11-01
2027-12-01

## How to use
Spain 2027 relocation and program plan
Sheets
Summary: counts of open, overdue, and due-soon items. Formulas, do not edit.
Deadlines: every dated item. Edit the yellow Status and Notes columns. Days left and highlighting update automatically: red is overdue, yellow is due within 14 days.
Monthly actions: the action items for each month. Edit Status and Notes.
Programs: the program tracker. Edit Status, Deadline, Missing items.
Income log: enter each month's gross deposits and the rate used. The sheet shows whether the month clears the visa threshold. The first row is an example, replace it.
Yellow cells are for you to edit. Everything else is either source data or a formula.
Dates marked Month only had no exact day in the source; the day is set to the 1st.
Confidence column: Confirmed means verified with the source on the date shown. Assumed means inferred and needs checking. Not verified means unknown.
Regenerating: this file is built from the markdown plan files in the spain2027 repo by scripts/build_plan_xlsx.py. If you edit here and also want the repo updated, share the edited file back.
Built 2026-09-16